May 3, 2006

Page 2

Transition to the New System

The integrated CIRTS/CMS application will be installed in one PSA at a time over a period of six months.   The tentative “go-live” schedule is attached (Attachment 4), while the timeframes are subject to change, the order of the AAAs is fixed.  As each area has the application installed, the screens of the new system will be unavailable to those offices already using the new integrated CIRTS system during the data load, however reporting and ad hoc queries will be available.  The process will begin at noon on the “go live” date, which will be on a Thursday.  The new system will be available on the following Monday.

#### User Administration

Your LAN Administrator is responsible for assigning user roles in the new system and providing them to the Information Technology office at Elder Affairs.  Passwords will be assigned and distributed to the LAN Administrators and CARES supervisors.  Details of this process will be communicated directly to the LAN Administrators.

User Training

LAN Administrators will be required to train all aging network users in their PSA on the new system.  There will be little change for end users.  The new system will have several new features and processes including the ability to transfer clients between PSAs, the ability to see CARES assessments and level of care determinations, as well as the ability for designated users to see client data from other PSAs.

Batch Transmission of Data Must Use EDI Protocol

The integrated CIRTS/CMS will not accept batch transmissions; all data exchange must be done using HIPAA compliant EDI transmissions.  We will provide specifications for the EDI transmissions to the LAN administrators upon request.

Oracle Discover and Ad-Hoc Reports May Require Changes

Any Oracle Discoverer reports developed by your Agency will need to be reviewed and modified to accommodate the new table structures and locations.   The changes required by the new system were reviewed at the last LAN Administrator meeting.   Table specifications are currently available from the Information Technology office at DOEA and a database is available for development of the new reports.

Installation of Required Workstation Software

Elder Affairs will provide a security certificate and a small software module for your LAN Administrators to install on each workstation that will access the combined CIRTS/CMS application.

Thank you for your assistance with making the CIRTS / CMS integration project a success.  As always, we appreciate your contribution to the team effort of providing quality services to the elders of Florida.

##### Attachment 1:  Distribution of Records to be verified by PSA

| PSA | Number of client records to verify for possible duplication |
| --- | --- |
| 1 | 224 |
| 2 | 270 |
| 3 | 639 |
| 4 | 799 |
| 5 | 706 |
| 6 | 987 |
| 7 | 975 |
| 8 | 500 |
| 9 | 933 |
| 10 | 966 |
| 11 | 1,751 |

Attachment 2:  Listing of CARES Office Contacts

Attachment 3:  Listing of Area Agency LAN Administrators

Attachment 4:  Tentative Go-Live Schedule for Integrated CIRTS / CMS Application

| Tentative Go-Live Date | AAA | Cares Offices |
| --- | --- | --- |
| May 18, 2006 | PSA2 | CARES2A, CARES2B |
| June 15, 2006 | PSA1 | CARES1 |
| June 29, 2006 | PSA8 | CARES8 |
| July 13, 2006 | PSA9 | CARES9A, CARES9B |
| July 27, 2006 | PSA5 | CARES5 |
| August 10, 2006 | PSA7 | CARES7A, CARES7B |
| August 24, 2006 | PSA4 | CARES4A, CARES4B |
| September 7, 2006 | PSA6 | CARES6A, CARES6B |
| September 21, 2006 | PSA3 | CARES3A, CARES3B |
| October 5, 2006 | PSA11 | CARES11A, CARES11B |
| October 26, 2006 | PSA10 | CARES10 |

# Text boxes

### MEMORANDUM

TO:		AAA Directors		NOTICE #: 050406-1-I-MIS

FROM:	Carole Green

Secretary

DATE:	May 3, 2006

SUBJECT:	Notice of Instruction:  AAA Activities related to the installation of the Integrated CIRTS / CMS software application

The purpose of this notice is to outline the activities required as a result of the integration of CMS and CIRTS.   DOEA has been working closely with your LAN Administrator.  This notice is to request your assistance in providing the resources necessary to insure a successful transition to our new system.

Data Synchronization and Cleanup

The integration of CMS and CIRTS includes the consolidation of the existing 18 CMS and 11 CIRTS databases into a single statewide database.  This consolidation requires the reconciliation of client records.

Clients who have moved between PSAs, as well as clients seen both by CARES and the aging network, will have multiple records.  Rules were developed to process records for duplicate Social Security numbers.   Ninety four percent of the clients that appeared in more then one database can be processed automatically.  However, there are 8,750 clients making 17,403 appearances in the databases that must be addressed manually. The distribution of clients by office is attached to this notice (Attachment 1).

Typically, the spelling of a name is too different for the computer program to treat as a match, so the client will need to be identified manually.   If it appears to be the same client in both databases, the record can remain to be processed automatically.  If it appears to be distinct clients with the same SSN, AAA and CARES staff will need to communicate to research the client and correct the records in CIRTS and CMS as appropriate.

During the consolidation of the databases, the demographics record from the database where the client was most recently assessed will be retained.  We will provide a list to your LAN Administrator of your portion of the 8,750 clients for you to verify that this will not cause any adverse effects.  The LAN Administrators were briefed on this process at our last statewide meeting.  A list of contacts at the CARES offices is attached (Attachment 2). The LAN administrators on the attached list (Attachment 3) will provide the initial point of contact at each AAA.

ttp://elderaffairs.state.fl.us

4040 ESPLANADE WAY

TALLAHASSEE

FLORIDA,  32399-7000

phone  850.414.2000

fax  850.414.2004

TDD  850.414.2001

# Carole Green

## SECRETARY

# Jeb bush

## GOVERNOR